## Meetings
P:Present | A:Absent | L:Late
S:Networked | I:Informed | N:Not Expected
CS1410 Group 16
|  |  | Attendance: |  |  |  |  | red means nothing really was done
|  | Date: | A.H | L.J | Y.M | H.N | J.O | Agenda: |  | Notes: |  | TODO:
Week 7 | Tutorial 7 | 2017-03-07 | P | A | I | P | A | Complete Analysis of coursework | . | wasn't abe to do much do to absence of other members | . | Create Design (CRC cards), Finish Design by week 8
| Meeting | 2017-03-07 | P | I | S | P | A | Assigning Roles and Starting Design | . | Tried to connect to Yusif by Skype, ran into multiple hardware issues with Mic/Camera, ended up not getting anything done so a repeat meeting was organized for the next day | . | .
| Meeting | 2017-03-08 | P | P | A | P | A | Re:Assigning Roles and Starting Design | . | Nearly completed analysis, discussed next actions | . | A.H: Abstraction from spec, Leen : Verb-Notes
Week 8 | Lab 7 | 2017-03-14 | P | A | A | I | A |  | . | No one attended so I went home | .
| Tutorial 8 | 2017-03-13 | P | A | A | P | A |  | . | H.N: Started UML | .
| Workshop 1 | 2017-03-19 | P | A | P | I | A | Learn and create UML diagrams | . | Created requirment analysis from abstracted information from the spec | .
Week 9 | Lab 8 | 2017-03-20 | P | I | P | P | L | Lectured the lecturer about the coursework | . | Created designs based on spec
| Tutorial 9 | 2017-03-21 | P | I | A | P | P |  | .
| Workshop 2 | 2017-03-22 | P | I | I | P | P | Listing all processes: Setting up Git and Trello | .
Week 10 | Lab 9 | 2017-03-27 | P | P | N | P | P |  | . | Hannah tried to make a GUI, Leen read the spec, Jovin revised… I couldn't think of anything to do | .
| Skype WS | 2017-04-01 | S | S | S | S | A |  | . | Yusif: UML , Hannah: draft Vehicle class, Adnaan: UserInputInterface & TextUI, Leen Junit test for UserInputInterface
| Meeting | 2017-04-03 | L | A | A | P | L | Explain design, FINISH UML! Plan timeline, assign tasks |  | Deadline for tasks set Friday
|  | 2017-04-07 | P | A | S | P | A | Finish UML, decide what to do during easter
EASTER |  | 2017-04-10
2017-04-30
Due 5th Mar
Note on E14: adnaan hussain: Phone&Laptop not working, assume same reason for previous missed attendence

## Profiles
Name | Adnaan Hussain | Leen Jacob | Yusif Malaika | Hannah Narme | Jovin Okwir
S:ID | 160111488 | 159033364 | 160228937 | 160074769 | 160109935
Email | Hussaa65 | Jacobln | Malaikay | Narmeh | Okwirj
M# | 07968751749 | 07428231802 | 07379460535 | 07756015634 | 07821238093
Java % | 99.2% | 78% | 83% | 75% | 40%
Preference/5
Documentation | 2 | 3 | 3 | 4 | 2
Writing | 1 | 3 | 2 | 4 | 4
CRC | 1 | 5 | 4 | 1 | 1
UML | 2 | 5 | 3 | 4 | 1
otherDiagrams | 4 | 5 | 3 | 1 | 4
Writing Spec | 3 | 2 | 5 | 3 | 3
Writing JavaDoc | 3 | 2 | 3 | 1 | 3
Writing JUnitTest | 2 | 2 | 2 | 2 | 1
Problem/Bug Solving | 5 | 3 | 4 | 3 | 1
Pseudocode | 2 | 3 | 3 | 3 | 1
Algorithims | 5 | 3 | 4 | 3 | 3
Programming | 5 | 4 | 5 | 4 | 2
Refactoring | 4 | 3 | 5 | 2 | 1
GUI Design | 5 | 1 | 4 | 2 | 1
GUI Implementation | 4 | 1 | 3.5 | 4 | 1
Tasks: | Adnaan Hussain | Leen Jacob | Yusif Malaika | Hannah Narme | Jovin Okwir
Petrol Station java | Pre-lim design | Noun-Verb | Pre-lim design | Connected GitHub | CRC | Complete | small-task
Petrol Station doc | Setup GitHub | Connected Trello | Connected Trello | Connected Trello | pump spec | Unsure
Petrol Station spec | Rewriting Spec | UI JTest | Connected GitHub | Noun-Verb | Connected GitHub | InProgress
Petrol Station manual test | Complete Design | Connected GitHub | finalizing UML | UML | Connected Trello | InComplete | DueTo:
Output java | Setup Trello |  |  | TextUI Java |  |  | Transferred
Output doc | help Finalize UML |  |  | Motorbike spec |  |  | Delay
Output spec | UI spec |  |  | Vehicle JTest |  |  | Errors
Output Jtest | UI java |  |  | R: Explain design |  |  | Abandoned
Simulation java | UI doc
Simulation doc | TextUI spec
Simulation spec | TextUI java
Simulation manual test | TextUI doc
R:UML Class | Vehicle+sub Spec
R: Simulation results | Vehicle+sub Java
R: results implication | Vehicle+sub Doc
R: list of source code
R: instuc to Build&Run
R: Export as pdf
update UML to lv1
UML:Sequence
Truck java
Truck doc
Truck spec
Truck Jtest
refactor Vehicle to support
GUI Wireframe
GUI java
GUI doc
GUI spec
GUI manual test
implement GUI to Simulation
implement shop into Vehicles
implement shop into Petrol Station
implement shop into Output
re-test everything
re-R:Explain design
R: changes
re-R:UML Class
R:UML sequence
re-R: Simulation results
re-R: results implication
re-R: list of source code
re-R: instuc to Build&Run
re-R: Export as pdf
Note on D28: adnaan hussain: Created System Archetechure for design to be based on and started creating Designs based on it ~ Did more acheteture
Note on H28: adnaan hussain: Created System Archetechure for design to be based on and started creating Designs based on it ~ Did more of the design work
Note on D30: adnaan hussain: Rewrote the spec in slightly different layout, and more details about the implementation
Note on J30: adnaan hussain: Wrote Noun-Verb design based on given Spec
Note on D31: adnaan hussain: see ReSpec
Note on J31: adnaan hussain: Mostly completed based on pre-lim design
Note on J32: adnaan hussain: didn't add Throwable to signature, Jdoc , and thrown message is vauge and undescriptive of error
Note on D37: adnaan hussain: Completed basic implementation

## Meeting 7-3
Agenda | Re:Assigning Roles and Starting Design | Location | MB205
|  | Date | 2017-03-07
Previous Items | N/A | Time | 16:00
Meeting Info | expected reading: coursework spec
Current Items
Notes | Nothing was done due to hardware faliures when trying to network with Yusif

## Meeting 8-3
Agenda | Re:Assigning Roles and Starting Design | Location | MB202
|  | Date | 2017-03-08
Previous Items | Incomplete: Assigning group roles, discussing the courswork, analysing the spec and assigning work | Time | 14:00
Meeting Info | expected reading: coursework spec
Current Items | Assigning Roles
Unable to do, due to not having all members at meeting. Also need to deside if we're going to use AGILE instead of fixed roles
discussing the courswork
Talked about the mechanics we could use to create the simulation and how we could use aspects from the Fox&Rabbit Simulation, A: plan to undersand how the Fox&Rabbit simulation works so maybe it's design could be used here.
Analysing Spec
Started to go over submition section of the coursework but didn't complete analysis, instead moved onto next topic
Assigning Work
Implied work people could do, but nothing was explicitly set
Notes | No one seams to like doing documentation, people enjoy programming more

## Meeting Template
Agenda | Location
Date
Previous Items | Time
Meeting Info
Current Items
Notes